## 20250313020000
Id | Type | Region | Navigation | Location | Description | Towpath closed? | Start date | End date | Link
28790 | Navigation Closure | Wales & South West | River Severn Navigation | River Severn Navigation - Lock 8 Holt Lock. | The delivery team have looked at several options to complete the works within the original schedule, but this is now not possible due to the set back we have already had because of flooding. Therefore a 2-week extension is required which means we are on site from the 23 September through to the 22 November 2024. | Yes | 2024-09-23T08:00:00+01:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28790-river-severn-navigation-lock-8-holt-lock
28758 | Navigation Closure | North West | Ribble Link | Lock No 4, Ashton on Ribble, Preston | The Rip Rap/Gabion baskets behind the flood weir at Lock 4 has been scoured out by flood water.The repair is to clear the debris, carry out repairs to the gabions and rip rap reinstatement, geotextile and topsoil/seeding. | No | 2024-09-30T08:00:00+01:00 | 2024-11-08T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28758-lock-no-4-ashton-on-ribble-preston
29084 | Advice | North West | Weaver Navigation | Dutton Large Lock, Bartington | Following on from our last update, this navigational restriction has now finished. We are still working on site so please take care when travelling through this section. | No | 2024-10-14T08:00:00+01:00 | 2025-02-11T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29084-dutton-large-lock-bartington
28749 | Navigation Closure | East Midlands | Leicester Line (Grand Union Canal) | Lock 35, Whetstone Lane Lock, Whetstone | We are pleased to advise that the works at Lock 35 Whetstone will be completed by Wednesday 15th January at 8am. | Yes | 2024-10-28T08:00:00+00:00 | 2025-01-15T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/28749-lock-35-whetstone-lane-lock-whetstone
28160 | Navigation Closure | West Midlands | Shropshire Union Canal | Clare's Culvert 70, Adderley | We are pleased to advise that we no longer need this closure. Ahead of the planned works we have undertaken grouting works to repair this leak without the need to dewater the navigation. This grouting has been more successful than anticipated and we will supplement the grouting with some other minor works that don’t need a closure. This will allow us to both remove the stoppage from the programme and to allocate the funding elsewhere to get other additional repairs completed. This means the navigation will no longer be closed at Clare's Culvert between the 4 November 2024 and the 6 December 2024 | No | 2024-11-04T08:00:00+00:00 | 2024-10-25T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28160-clares-culvert-70-adderley
28162 | Navigation Closure | North West | Ribble Link | Lock 5, Lea, Preston | We are pleased to advise that the repair works to Lock 5, Lea, Preston, have been completed ahead of schedule. | No | 2024-11-04T08:00:00+00:00 | 2024-11-26T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28162-lock-5-lea-preston
28164 | Navigation Closure | North West | Rochdale Canal | Lock 69, Newton Heath, Failsworth | We are pleased to advise, the works to Lock 69, Newton Heath have been completed ahead of schedule. | No | 2024-11-04T08:00:00+00:00 | 2024-12-18T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28164-lock-69-newton-heath-failsworth
28165 | Navigation Restriction | West Midlands | Grand Union Canal | Longhole Viaduct - High Speed 2 over the Grand Union Canal, near Ufton | We have been advised that HS2 are ahead of schedule and have completed this section of planned works. Therefore, the canal will no longer be closed to facilitate these works. | No | 2024-11-04T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28165-longhole-viaduct-high-speed-2-over-the-grand-union-canal-near-ufton
28168 | Navigation Closure | North West | Shropshire Union Canal | Pipeline crossing next to Bridge 130, Mollington | Contractors working for Cadent gas have not been able to secure a road closure from the council for the original planned closure dates. Therefore they would like to revise them. The new closure dates are from the 4 November 2024 through to the 15 November 2024. The towpath will remain open. | No | 2024-11-04T08:00:00+00:00 | 2024-11-15T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28168-pipeline-crossing-next-to-bridge-130-mollington
29961 | Navigation Closure | London & South East | Aylesbury Arm (Grand Union Canal) | Lock 15, Aylesbury | A navigation closure is required to replace the top end single and bottom end mitres on the lock gates. These works will take place from the 04 November 2024 to the 19 December 2024. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29961-lock-15-aylesbury
28173 | Navigation Closure | North West | Leeds & Liverpool Canal | Service Crossings, attached to Rishton Bridge 108A | A stoppage is required to allow contractors to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2024-11-04T08:00:00+00:00 | 2024-11-18T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28173-service-crossings-attached-to-rishton-bridge-108a
28181 | Navigation Closure | Yorkshire & North East | Bank Dole Cut | Pipe crossing adjacent to Trundles Lane Bridge, Knottingley | Scaffolding blocking waterway required for gas pipeline refurbishment | No | 2024-11-04T08:00:00+00:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28181-pipe-crossing-adjacent-to-trundles-lane-bridge-knottingley
28188 | Navigation Closure | West Midlands | Shropshire Union Canal | Tyrley Lock 4, Market Drayton | A navigation and towpath closure are required for masonry repairs to the offside chamber wall, towpath side. | Yes | 2024-11-04T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28188-tyrley-lock-4-market-drayton
28196 | Navigation Closure | London & South East | Grand Union Canal | HS2 Colne Valley Viaduct, 500m south of Moorhall Road, Denham | We have been advised that HS2 can now do this part of their construction works as a series of overnight closures. Therefore, the canal and towpath will no longer be closed to facilitate these works. | Yes | 2024-11-04T08:00:00+00:00 | 2024-08-28T14:00:00+01:00 | https://canalrivertrust.org.uk/notices/28196-hs2-colne-valley-viaduct-500m-south-of-moorhall-road-denham
28201 | Navigation Closure | West Midlands | Stourbridge Canal | Lock 6, Stourbridge | A navigation and towpath closure are required for top and bottom lock gate replacements. We will also be doing a full lock ladder rebuild, Lock chamber brickwork repairs and wingwall leak repairs. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28201-lock-6-stourbridge
28211 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 51, Wootton Rivers | Due to the deferral of Lock 55, the closure area for this stoppage has changed. The new closure area will be from Lock 51 through to lock 54. Please make sure any craft are moved from the area by Saturday 2 November, ready for the works to begin on the 4 November 2024. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28211-lock-51-wootton-rivers
28213 | Navigation Closure | London & South East | River Stort | Feakes Lock 7, Sawbridgeworth | We are pleased to advise, the repair works to Feakes Lock (7) will be completed today, 13 December 2024. | No | 2024-11-04T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28213-feakes-lock-7-sawbridgeworth
28732 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 60 Johnson's Hillock | A stoppage is required to carry out works to prevent leakage through the lock chamber walls and head forebay. | No | 2024-11-04T08:00:00+00:00 | 2024-11-15T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28732-lock-60-johnsons-hillock
28736 | Navigation Closure | North West | Rochdale Canal | Key Lane Lock 64, offside Landing, Middleton, Manchester. | These works are no longer going ahead within this winter works programme as site constraints now make the planned method of construction unworkable in the time available. We will look to reschedule them in a future winter programme using an alternative construction method. This means the navigation and towpath between locks 63 and 81 will remain open between the 4 November 2024 to the 19 December 2024. | Yes | 2024-11-04T08:00:00+00:00 | 2024-10-24T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28736-key-lane-lock-64-offside-landing-middleton-manchester
28737 | Navigation Closure | North West | Rochdale Canal | Lock 65 Alfred street, Failsworth (between Oldham and Manchester) | We are pleased to advise, the works at Lock 65, Alfred Street, have been completed ahead of schedule. | No | 2024-11-04T08:00:00+00:00 | 2024-12-03T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/28737-lock-65-alfred-street-failsworth-between-oldham-and-manchester
28237 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 52, Heathy Close, Wootton Rivers | Due to the deferral of Lock 55, the closure area for this stoppage has changed. The new closure area will be from Lock 51 through to lock 54. Please make sure any craft are moved from the area by Saturday 2 November, ready for the works to begin on the 4 November 2024. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28237-lock-52-heathy-close-wootton-rivers
28750 | Navigation Closure | East Midlands | Grand Union Canal | Lock 3 Braunston (Braunston) | For water control reasons, we have had to widen the closure area for these planned works. The new closure area is from Lock 2 through to Lock 6, Top Lock. The closure dates remain the same; 4 November 2024 through to the 19 December 2024. Please note we will only be dewatering Lock 3, Braunston. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28750-lock-3-braunston-braunston
28754 | Navigation Closure | North West | Llangollen Canal | Baddiley Lock 2, Wrenbury Heath | We are pleased to advise, the works to Lock 2, Baddiley have been completed ahead of schedule. | No | 2024-11-04T08:00:00+00:00 | 2024-12-16T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28754-baddiley-lock-2-wrenbury-heath
28243 | Navigation Closure | West Midlands | Oxford Canal | Napton Lock 11, Napton on the Hill | A navigation and towpath closure is required for leak repairs on the pound sidewall. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T17:00:00+00:00 | https://canalrivertrust.org.uk/notices/28243-napton-lock-11-napton-on-the-hill
28244 | Navigation Closure | London & South East | Oxford Canal | Middle Bridge 145 | Oxfordshire County Council no longer need this planned closure. Therefore, in reference to this notice, the navigation and towpath will be open at Middle Bridge 145 between the 4 November 2024 and the 17 November 2024. | Yes | 2024-11-04T08:00:00+00:00 | 2024-10-21T16:00:00+01:00 | https://canalrivertrust.org.uk/notices/28244-middle-bridge-145
29268 | Navigation Closure | West Midlands | Shropshire Union Canal | Between Bridge 24 & 25, High Onn, Shropshire Union Canal | We are pleased to advise that the works have been completed ahead of schedule and the navigation has reopened. | No | 2024-11-04T08:00:00+00:00 | 2024-11-21T13:00:00+00:00 | https://canalrivertrust.org.uk/notices/29268-between-bridge-24-25-high-onn-shropshire-union-canal
28248 | Navigation Closure | London & South East | Oxford Canal | Shipton Flood Gate, Shipton-on-Cherwell | A stoppage is required to carry out replacement of the flood gates, and repair to the offside wharf wall. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28248-shipton-flood-gate-shipton-on-cherwell
28252 | Navigation Closure | West Midlands | Staffordshire & Worcestershire Cnl | Bumble Hole Lock 22, Smestow | A navigation and towpath closure is required for top and bottom end lock gate replacement. We will also be doing a full lock ladder rebuild. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28252-bumble-hole-lock-22-smestow
28764 | Navigation Closure | North West | Weaver Navigation | Anderton Boat Lift, Northwitch | A stoppage is required to carry out main hydraulic cylinder modifications and annual maintenance to the boat lift. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28764-anderton-boat-lift-northwitch
29085 | Navigation Closure | West Midlands | Coventry Canal | Lock 3 Coventry Canal | A navigation and towpath closure are required for top end and bottom end mitre gate replacements. We will also be repairing the lock ladder hoops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29085-lock-3-coventry-canal
29089 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Lock 1, River Lock, Canal Wharf, Leeds | The works at this site have been delayed causing a 1 week extension. When re-cutting the stop log grooves, we discovered the existing stone was in very poor condition. This has meant we have had to finish cutting the grooves by hand which is taking longer than originally planned. Efforts have been made to speed up the process by using alternative equipment and additional manpower, but unfortunately, we are still behind schedule. The new planned opening date for this closure is the 15 February 2025. | Yes | 2024-11-04T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29089-lock-1-river-lock-canal-wharf-leeds
29093 | Navigation Closure | West Midlands | Oxford Canal | Bridge 130, Knotts Bridge | We are pleased to advise, the works at Bridge 130, Knotts Bridge, have been completed ahead of schedule. Works to repair the towpath will commence in the new year. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29093-bridge-130-knotts-bridge
29095 | Navigation Closure | Yorkshire & North East | Sheffield & South Yorkshire Nav | Doncaster Lock, Doncaster | A navigation and towpath closure are required to repair the detached downstream sluice and the damaged frame and upstream ground paddle. Works will also be carried out to rectify the severe boil on the upstream cills and replace 5 Lock ladders. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29095-doncaster-lock-doncaster
29096 | Navigation Closure | Yorkshire & North East | Sheffield & South Yorkshire Nav | Swinton Lock, Swinton, South Yorkshire. | A navigation and towpath closure are required to replace the bottom lock gates and cills. We will also be replacing 8 lock ladder tops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29096-swinton-lock-swinton-south-yorkshire
29102 | Navigation Closure | London & South East | Hertford Union Canal | Accommodation Bridge 10, footbridge, Hackney Wick, London. | After receiving some feedback, we would like to clarify the detail of this notice - This closure is to facilitate the safe demolition of a wall adjacent to the towpath and lock 3, Bottom Lock. We had originally planned to use this closure to remove accommodation bridge 10 but this will not be going ahead at this time due to delays in getting a Section 38 agreement finalised for its replacement. | Yes | 2024-11-04T08:00:00+00:00 | 2024-11-08T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29102-accommodation-bridge-10-footbridge-hackney-wick-london
29933 | Navigation Closure | Wales & South West | River Severn Navigation | Lock 2, Gloucester Lock, The Docks, Gloucester | Work to strengthen the existing stop log metal channel, in the river side of Gloucester lock has been established. The navigation will be closed from the 4 November through to the 8 November 2024 (inclusive), open for the weekend (9 and 10 November) and closed again on the 11 November 2024 for these works to be completed. | No | 2024-11-04T08:00:00+00:00 | 2024-11-11T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29933-lock-2-gloucester-lock-the-docks-gloucester
28143 | Navigation Closure | West Midlands | Dudley No 1 Canal | Delph Lock 6, Brierley Hill | A navigation and towpath stoppage are required for top and bottom end gate replacements. We will also be repairing the brickwork under the coping stones and anchor stone. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28143-delph-lock-6-brierley-hill
28145 | Navigation Closure | North West | Shropshire Union Canal | Hack Green, Lock 1, Audlem | A stoppage is required for repair works to be done to the pointing & brickwork, lock ladder and Lock gate liner. | No | 2024-11-04T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28145-hack-green-lock-1-audlem
28147 | Navigation Closure | West Midlands | Coventry Canal | Lock 11, Atherstone | A navigation and towpath stoppage are required for top end and bottom end mitre gate replacements. We will also be repairing the lock ladder hoops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28147-lock-11-atherstone
28149 | Navigation Closure | Yorkshire & North East | Selby Canal | A19 Burn Bridge 3, Brayton | Please be advised, the Third Party works at A19 Burn Bridge 3, have been completed ahead of schedule. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-04T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/28149-a19-burn-bridge-3-brayton
28151 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bank Newton, lock 37, 5th lock | A stoppage is required to allow Lock gate replacement and repair works. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28151-bank-newton-lock-37-5th-lock
28155 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bank Newton, lock 41, Top lock | A stoppage is required for tail gate replacement and lock chamber repairs. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28155-bank-newton-lock-41-top-lock
28156 | Navigation Closure | North West | Rochdale Canal | Lock 39, Timbercliffe | A stoppage is required for repairs to the top lock gates & cills. | No | 2024-11-04T08:00:00+00:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28156-lock-39-timbercliffe
29180 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Lock 8, Mayroyd | A Navigational closure to inspect and repair the boil on the tail gate. | No | 2024-11-04T08:00:00+00:00 | 2024-12-02T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29180-lock-8-mayroyd
28742 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bridge 195 Booth's swing Bridge between Bingley and Silsden near Keighley. | Further to our update yesterday, we are very pleased to advise that the works have been completed, the bridge is now operational and the navigation has reopened. | No | 2024-11-06T08:00:00+00:00 | 2024-11-21T13:00:00+00:00 | https://canalrivertrust.org.uk/notices/28742-bridge-195-booths-swing-bridge-between-bingley-and-silsden-near-keighley
29932 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Cowling Swing bridge, Silsden | Following the installation of Cowling swing bridge in February 2024, It is believed the bearings are damaged and need replacing. To safely carry out the works, the bridge will have to be moved into the canal closed position and jacked up to be able to remove the pintel and have the bridge fully supported on its bearing points for the duration of the works. We will be aligning this closure with the existing one at Bridge 195, Booths swing bridge. The closure will be from the 6 November 2024 through to the 20 November 2024. | No | 2024-11-06T08:00:00+00:00 | 2024-11-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29932-cowling-swing-bridge-silsden
28714 | Navigation Closure | West Midlands | Titford Canal | Tat Bank Bridge, Oldbury | A stoppage is required for repairs to the Highways bridge. Scaffolding and bridge encapsulating will be needed to complete these works. | Yes | 2024-11-11T08:00:00+00:00 | 2024-11-30T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28714-tat-bank-bridge-oldbury
28210 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 77, of the Wigan Flight, Wigan | Within the Wigan Flight we are working on two Locks, Lock 75 and Lock 77. For Health and Safety reasons we will be closing the Wigan flight from Lock 65 through to Lock 85. We will be locking this section of navigation on the 11 November through to the 19 December to facilitate the wash wall repair works. Apologies for any confusion caused. | No | 2024-11-11T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28210-lock-77-of-the-wigan-flight-wigan
28241 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 75 of the Wigan Flight, Wigan | Within the Wigan Flight we are working on two Locks, Lock 75 and Lock 77. For Health and Safety reasons we will be closing the Wigan flight from lock 65 through to lock 85. We will be locking this section of navigation on 11 November through to the 19 December to facilitate the wash wall repair works. | No | 2024-11-11T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28241-lock-75-of-the-wigan-flight-wigan
28251 | Navigation Closure | West Midlands | Stourbridge Canal | Stourton Lock 3, Stourton | A navigation and towpath closure is required to replace the top end single and bottom end mitres on the lock gates. We will also be extending the lock ladder and replacing the hoops. | Yes | 2024-11-11T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28251-stourton-lock-3-stourton
29176 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 61 Johnson's Hillock | The repair works to Lock 61 have now been completed but the flight is still closed as the team are working at lock 62. | No | 2024-11-11T08:00:00+00:00 | 2024-12-03T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29176-lock-61-johnsons-hillock
29944 | Navigation Closure | North West | Shropshire Union Canal | Lock 14, Lower Lock & Lock 15, Upper Lock, Bunbury | We are pleased to advise, the repair works to Lock 14 and Lock 15 Bunbury, have been completed ahead of schedule. | No | 2024-11-11T08:00:00+00:00 | 2024-12-03T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/29944-lock-14-lower-lock-lock-15-upper-lock-bunbury
29177 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 62 Johnson's Hillock | The work at this location has been extended. Whilst working on the lock flight it became apparent that 30 meters of wash wall below lock 58 needed an emergency repair to stop any overtopping into the culvert. The Trust made the decision to do this work now to prevent us closing the navigation again in the near future. Unfortunately, this has impacted the planned works on the lock flight and delayed this closure by 10 days. The new end date for this closure will be the 17 December 2024. | No | 2024-11-11T08:00:00+00:00 | 2024-12-17T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29177-lock-62-johnsons-hillock
28161 | Navigation Closure | North West | Rochdale Canal | Lock 41, Littleborough | We are pleased to advise that the repair works to Lock 41 have been completed ahead of schedule. | No | 2024-11-18T08:00:00+00:00 | 2024-11-26T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28161-lock-41-littleborough
28723 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Between Bridge 110 and Bridge 114, Llangattock | We apologise that the planned start date for the works has been delayed. The revised date for commencement is 18 November 2024. The planned end date for the works remains unchanged at 20 December 2024. | No | 2024-11-18T08:00:00+00:00 | 2024-12-20T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/28723-between-bridge-110-and-bridge-114-llangattock
28744 | Navigation Closure | North West | Shropshire Union Canal | Sluice near Bridge 91, Marsh Lane, Nantwich (works on culvert 49 going on) | We are pleased to advise that the works have been completed ahead of schedule and the navigation has reopened. | No | 2024-11-18T08:00:00+00:00 | 2024-11-25T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28744-sluice-near-bridge-91-marsh-lane-nantwich-works-on-culvert-49-going-on
29178 | Navigation Closure | North West | Bugsworth Arm (Peak Forest Canal) | Bugsworth Basin Whaley Bridge | A navigational closure is required to rebuild the stone wash wall and reset the coping stones. As part of this work, we will be installing two fabric dams. | No | 2024-11-18T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29178-bugsworth-basin-whaley-bridge
28245 | Navigation Closure | London & South East | Oxford Canal | Middle Bridge 145 | Oxfordshire County Council no longer need this planned closure. Therefore, with reference to this notice, the navigation will be open at Middle Bridge 145 between the 18 November 2024 and the 29 November 2024 | No | 2024-11-18T20:00:00+00:00 | 2024-10-21T06:00:00+01:00 | https://canalrivertrust.org.uk/notices/28245-middle-bridge-145
28766 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Llanfoist Embankment, Bridge 95A - Bridge 95 | The works at this location have been delayed due to a delay with approvals and contractors confirming the works detail. The closure will now start on the 21 November 2024 and run through to the 20 December 2024. | Yes | 2024-11-21T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28766-llanfoist-embankment-bridge-95a-bridge-95
28175 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Lock 17, near Todmorden | A stoppage is required to allow Lock gate leakage repairs and gate fender repair works. | No | 2024-11-25T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28175-lock-17-near-todmorden
28724 | Navigation Closure | West Midlands | Llangollen Canal | Springhill Bridge 41, Whitchurch | These works are no longer going ahead within this winter works programme; we are hopeful that they can be delivered next winter. This means the navigation and towpath, in reference to this notice, are now open at Springhill Bridge 41 from the 25 November 2024 to the 20 December 2024. | Yes | 2024-11-25T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28724-springhill-bridge-41-whitchurch
28725 | Navigation Closure | Yorkshire & North East | Bank Dole Cut | Bank Dole Lock 5, located on the edge of Knottingley | A stoppage is required to stop the leak at the end of the lock island into the river and from the lock walls into the lock chamber.We will inject grout into the lock chamber walls to fill the voids and hopefully prevent any future leakage paths. | No | 2024-11-25T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28725-bank-dole-lock-5-located-on-the-edge-of-knottingley
28745 | Navigation Closure | North West | Shropshire Union Canal | Sluice 7, Moss Hall, by Bridge 80, Audlem | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2024-11-25T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28745-sluice-7-moss-hall-by-bridge-80-audlem
28238 | Navigation Closure | West Midlands | Llangollen Canal | Hassells Bridge 33, Whitchurch | We are pleased to advise, the works at Hassells Bridge 33, have been completed ahead of schedule. | Yes | 2024-11-25T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28238-hassells-bridge-33-whitchurch
29088 | Navigation Closure | North West | Leeds & Liverpool Canal | Yorkshire Street Aqueduct, Burnley | A navigation and towpath closure are required to enable a comprehensive inspection of the canal wash walls and bed. This will involve the installation of two fabric dams, one at Finsley Gate and one at Yorkshire Street aqueduct, followed by a fish rescue and then de-watering. | Yes | 2024-11-25T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29088-yorkshire-street-aqueduct-burnley
28158 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Bridge 25, Shaw Wood Bridge, Todmorden | A stoppage is required for refurbishment of the gas main attached to Shaw Wood bridge. This will require scaffolding which will block the navigation | No | 2024-11-25T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28158-bridge-25-shaw-wood-bridge-todmorden
28159 | Navigation Closure | North West | Rochdale Canal | Lock 40 Punchbowl, Littleborough | We are pleased to advise, the repair works to Lock 40, Punchbowl have been completed ahead of schedule. | No | 2024-11-25T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28159-lock-40-punchbowl-littleborough
28166 | Navigation Closure | West Midlands | Oxford Canal | High Speed 2 viaduct over Oxford Canal Wormleighton | A navigation and towpath stoppage are required for construction of a new viaduct for High Speed 2. A towpath diversion will be in place. | Yes | 2024-12-02T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28166-high-speed-2-viaduct-over-oxford-canal-wormleighton
28240 | Navigation Closure | North West | Glasson Branch (Lancaster Canal) | Lock 3, Near Upper Thurnham | We apologise that we have been unable to start the work as planned due to the sudden onset of colder weather which affects the setting of the lime mortar which will be used in the reinstatement and pointing works. The work will now commence on 02/12/2024 with a revised end date of 13/12/2024. | No | 2024-12-02T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28240-lock-3-near-upper-thurnham
29092 | Navigation Closure | East Midlands | Trent & Mersey Canal | Lock 1 Derwent Mouth, Shardlow | Further to the notice below, the leak repair works to Lock 1, Derwent Mouth have been completed. The Lock gates are currently planned to be replaced within another winter programme. | Yes | 2024-12-02T08:00:00+00:00 | 2024-12-11T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/29092-lock-1-derwent-mouth-shardlow
29943 | Navigation Closure | North West | Shropshire Union Canal | Lock 10 Audlem | We would like to advise you of this additional closure to the Winter Works Programme. Repair works are needed to the top gates and paddles of Lock 10, Audlem. We will be closing the flight from Lock 1 through to Lock 10 for safety reasons, Lock 12 to 15 will remain open. These works will take place as a navigational closure from the 2 December 2024 to the 6 December 2024. | No | 2024-12-02T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29943-lock-10-audlem
29945 | Navigation Closure | North West | Shropshire Union Canal | Lock 10, Wharton's Lock, near Chester | The repair works to Lock 10, Wharton's lock, will now commence on the 2 December 2024 and run through to the 6 December 2024. The towpath will remain open. | No | 2024-12-02T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29945-lock-10-whartons-lock-near-chester
30070 | Navigation Closure | London & South East | Hertford Union Canal | Accommodation Bridge 10, Footbridge, Hackney Wick, London | To improve local pedestrian and cycle infrastructure over the canal in Hackney Wick. The existing footbridge at the junction of the Hertford Union Canal and the River Lea is being retired and replaced with a higher capacity structure. The works will involve closing the canal and the towpath overnight between the hours of 11pm - 6am over 3 night on 02/12/2024, 03/12/2024 and 04/12/2024 so that the bridge span can be safely lifted away into the building site to the North of the canal. On the approach from the South the canal can be closed from the Lock 1 Top Lock winding hole. The towpath will be closed from the ramp at Bridge 6, Wick Lane and the ramp at Bridge 11, Carpenters Road. Towpath moorings directly beneath the bridge will be suspended but access can be maintained to areas either side with marshalling at the towpath diversion points. | No | 2024-12-02T23:00:00+00:00 | 2024-12-05T06:00:00+00:00 | https://canalrivertrust.org.uk/notices/30070-accommodation-bridge-10-footbridge-hackney-wick-london
28253 | Navigation Closure | West Midlands | Staffordshire & Worcestershire Cnl | Park Gate Lock 40, Penkridge | A navigation and towpath closure is required to reset ground paddle stand on the lock. | Yes | 2024-12-09T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28253-park-gate-lock-40-penkridge
28191 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Brecon Basin, Brecon | A stoppage is required to repair the copings in Brecon Basin. | No | 2025-01-02T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28191-brecon-basin-brecon
28208 | Navigation Closure | West Midlands | New Mainline, Spon Lane Locks | Bromford Junction, Oldbury | We are pleased to advise that Network Rail are now able to undertake these works without closing the navigation and towpath, therefore they will now be open for the duration of the project. | Yes | 2025-01-02T08:00:00+00:00 | 2024-09-13T00:00:00+01:00 | https://canalrivertrust.org.uk/notices/28208-bromford-junction-oldbury
28721 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Between Bridge 76 and Bridge 88, Llanover | A stoppage is required for Investigation and clay repair to the canal bank. We will also be doing repairs to culvert 46 (not 48 as written on the original notice) Please note everything else about this closure remains the same. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/28721-between-bridge-76-and-bridge-88-llanover
28217 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 33, Caen Hill Flight | A stoppage is required to carry out replacement of the bottom lock gates, along with other packages of work along the flight. Locks 33 and 40 will be done in succession. The whole flight of locks will be closed to eliminate the risk of flooding the site. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28217-lock-33-caen-hill-flight
28218 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 40, Caen Hill Flight | Having reviewed the risk assessment for the works involved, we need to widen the closure area. The closure area will now be from Lock 50, Kennet Top Lock through to Lock 28, Devizes Lock. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28218-lock-40-caen-hill-flight
28752 | Navigation Closure | North West | Llangollen Canal | Bache House Bridge 2, Nantwich | The works at Bache House Bridge 2, have been completed ahead of schedule. This means the navigation is no longer closed to facilitate these works. | Yes | 2025-01-02T08:00:00+00:00 | 2025-02-21T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/28752-bache-house-bridge-2-nantwich
30342 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Llanfoist Embankment, Bridge 95A - Bridge 95 | Further to the notice below, please be aware that there is another piece of work coinciding within this area, between bridges 95A and 96. Please follow this link for more information Llanfoist Embankment, Bridge 95A - Bridge 96 ¦ Canal & River Trust | Yes | 2025-01-02T08:00:00+00:00 | 2025-02-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30342-llanfoist-embankment-bridge-95a-bridge-95
28163 | Navigation Closure | West Midlands | Oxford Canal | High Speed 2 Viaduct over Oxford Canal Wormleighton | We have been advised that HS2 are ahead of schedule and have already completed this section of planned works. Therefore, the canal and towpath will remain open. | Yes | 2025-01-06T08:00:00+00:00 | 2025-01-06T13:00:00+00:00 | https://canalrivertrust.org.uk/notices/28163-high-speed-2-viaduct-over-oxford-canal-wormleighton
28167 | Navigation Closure | North West | Huddersfield Narrow Canal | Offside canal embankment protection work. Nearest structure is Bridge 71 Wool Road. Diggle | A stoppage is required for offside embankment wash wall repairs. | No | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28167-offside-canal-embankment-protection-work-nearest-structure-is-bridge-71-wool-road-diggle
28169 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 1 East, Stanley Dawson Lock, Huddersfield | The works at this location have been disrupted and delayed by snow and ice. We have now dewatered the lock and have a clear understanding on the scope of the works so are able to give accurate timescales. The new planned opening date for this closure is the morning of the 08 February 2025 | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28169-lock-1-east-stanley-dawson-lock-huddersfield
28170 | Navigation Closure | North West | Macclesfield Canal | Red Bull Aqueduct, Kidsgrove | A stoppage is required to carry out brickwork repairs to try and stop leakage onto road below. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28170-red-bull-aqueduct-kidsgrove
28172 | Navigation Closure | North West | Huddersfield Narrow Canal | Service Crossings, attached to Bridge 87, Manchester Road Bridge | A stoppage is required to allow contractors to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2025-01-06T08:00:00+00:00 | 2025-01-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28172-service-crossings-attached-to-bridge-87-manchester-road-bridge
28176 | Navigation Closure | West Midlands | Dudley No 2 Canal | Wright's bridge, Blackheath | Despite our best efforts the works to Wrights bridge and Smiths bridge need to be extended. Whilst doing improvement works to the beam connections on Smiths bridge we had to undertake additional materials testing on the bridge. Once stripped back, the heritage beams on Wrights bridge were found to be in a much worse condition than we originally anticipated which has meant we’ve had to amend the works design to use new beams instead of the old ones. Unfortunately, this has pushed the programme out by two weeks. Whilst we will have to extend the works beyond the 14 March, we will adjust the final elements of the work to allow for safe navigation before 8:00 and after 16:45. The full navigational closure will finish on the 14 March when it becomes a navigational restriction through to the 28 March 2025. We apologise for any inconvenience this may cause. *Please note the status of this web notice will change to navigational restriction on the 15 March. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-28T16:45:00+00:00 | https://canalrivertrust.org.uk/notices/28176-wrights-bridge-blackheath
28186 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Red Doles Lock 9, Huddersfield | A stoppage is required to replace the downstream Lock gates and cills, replace a broken top ground paddle and re-bed the Lock copings and re-point the Lock walls. | No | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28186-red-doles-lock-9-huddersfield
28187 | Navigation Closure | Yorkshire & North East | Sheffield & Tinsley Canal | Tinsley Lock 12, Sheffield. | All the lock gate works at Lock 12 have been completed with only the piled cofferdam needing to be removed. We had anticipated our specialist contractor would be able to extract the sheet piles from Tuesday of this week, meaning that the lock stoppage would be open on time. However, when the extraction works commenced it quickly became apparent that the piles could not be removed. We therefore need to bring in a diving contractor to burn off the sheet piles at bed level so the cofferdam can be removed. This requires a safe method of operation to be established and for the diving team to become available. Regrettably, this now means the stoppage will need to be extended until 19 March. We will work with the contractor to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. | No | 2025-01-06T08:00:00+00:00 | 2025-03-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28187-tinsley-lock-12-sheffield
28190 | Navigation Closure | Yorkshire & North East | Chesterfield Canal | Worksop town Lock approach wall, Bassetlaw, Worksop | After works by the third party started on site it became clear that more of the wall was damaged than was originally thought. This means more of the wall has had to be taken down and will now need rebuilding. Unfortunately, this means the closure will need to be extended to the 9 April to facilitate these works. We have worked with the third party contractors who will focus on rebuilding the wall up to normal water line to allow the closure to be lifted. Once the navigation has been rewatered the other part of the wall rebuild will then continue under a navigation width restriction with a potential 20 mins delay whilst we move equipment out of the way. We are working closely with the third party contractors who are working extended hours to complete these works and will continue to do so in the hope that we can bring this closure forward. | Yes | 2025-01-06T08:00:00+00:00 | 2025-04-09T16:00:00+01:00 | https://canalrivertrust.org.uk/notices/28190-worksop-town-lock-approach-wall-bassetlaw-worksop
28194 | Navigation Closure | West Midlands | Trent & Mersey Canal | Shadehouse Lock 19, Fradley | A navigation and towpath stoppage are required for bottom end mitre gate replacements and Lock ladder hoops and associated brickwork repairs. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28194-shadehouse-lock-19-fradley
28195 | Advice | East Midlands | River Trent | Mill Bridge 20, Access bridge to Newark Repair Yard, Newark | The scaffolding has now been removed so this restriction is no longer needed. We will still be on site continuing with the rest of the works so please proceed with care. | No | 2025-01-06T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28195-mill-bridge-20-access-bridge-to-newark-repair-yard-newark
28710 | Navigation Closure | West Midlands | Dudley No 2 Canal | Smith's bridge, Blackheath | Despite our best efforts the works to Wrights bridge and Smiths bridge need to be extended. Whilst doing improvement works to the beam connections on Smiths bridge we had to undertake additional materials testing on the bridge. Once stripped back, the heritage beams on Wrights bridge were found to be in a much worse condition than we originally anticipated which has meant we’ve had to amend the works design to use new beams instead of the old ones. Unfortunately, this has pushed the programme out by two weeks. Whilst we will have to extend the works beyond the 14 March, we will adjust the final elements of the work to allow for safe navigation before 8:00 and after 16:45. The full navigational closure will finish on the 14 March when it becomes a navigational restriction through to the 28 March 2025. We apologise for any inconvenience this may cause. *Please note the status of this web notice will change to navigational restriction on the 15 March. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-28T16:45:00+00:00 | https://canalrivertrust.org.uk/notices/28710-smiths-bridge-blackheath
28199 | Navigation Closure | West Midlands | Caldon Canal | Sluice 6, between bridges 38 & 39, Denford | These works are no longer going ahead within this winter works programme; we are hopeful that they can be delivered in 2026 via a 3rd party funder. This means the navigation and towpath, in reference to this notice, are now open between bridge 38 and 39 from the 6 January 2025 to 24 January 2025. | Yes | 2025-01-06T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28199-sluice-6-between-bridges-38-39-denford
28206 | Towpath Closure | London & South East | Grand Union Canal | Bridge 108, Chelmscote, near Stoke Hammond | The dams will be removed at Chelmscote Bridge 108 tomorrow (14th February) reopening the navigation as planned. Please note, towpath works will continue until the 26 February 2025. A diversion is in place. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-26T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28206-bridge-108-chelmscote-near-stoke-hammond
28728 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 5 East, Paddock Foot Lock. | The works at Lock 5 East, Paddock Foot Lock, have been removed from the programme due to reprioritisation within our national grouting programme. | Yes | 2025-01-06T08:00:00+00:00 | 2025-01-16T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28728-lock-5-east-paddock-foot-lock
28730 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 4 West, Stalybridge | A stoppage is required to carry out head and tail lock gate replacements | No | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28730-lock-4-west-stalybridge
28731 | Navigation Closure | North West | Lancaster Canal | Culvert 59, near Blind Lane Bridge 115, Hest Bank | The works to Culvert 59 near Blind Lane Bridge, have been completed ahead of schedule. This means the navigation and towpath are no longer closed to facilitate these works. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28731-culvert-59-near-blind-lane-bridge-115-hest-bank
28741 | Navigation Closure | Yorkshire & North East | Aire & Calder Navigation Main Line | Ferrybridge lock flood gates, in Ferrybridge | Unfortunately, we have received a further extension request for Ferrybridge lock on the Aire and Calder. It was due to finish today, but an extension has been requested for the 12th of March. Despite our best efforts, including working weekends, site difficulties with fitting the tail cills, fendering and fitting the original walkboards to the gates have caused further delays to the original end date and dismantling site. With us now reliant on the scaffold removal on Monday 10th March and the divers returning on Tuesday 11th to facilitate the stop plank dam removal, we have had to reassess the opening date. This will now be by 4pm on Wednesday 12th March 2025. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-12T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28741-ferrybridge-lock-flood-gates-in-ferrybridge
28235 | Navigation Closure | London & South East | Grand Union Canal | Lock 65, Apsley, Near Hemel Hempstead | Due to the need to lower water levels to complete the lock gate fitting work to lock 65 Apsley, the levels in the pound below the works have been affected leaving some boats stuck for short periods of time. To alleviate this, we are going to extend the closure area of these works to include lock 66. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28235-lock-65-apsley-near-hemel-hempstead
28760 | Towpath Closure | West Midlands | Trent & Mersey Canal | Star Lock 27, Stone | Following on from our last update, this navigational closure has now finished. Please note the towpath will remain closed until the 14 February 2025. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28760-star-lock-27-stone
28249 | Navigation Closure | London & South East | Regent's Canal | Lock 7, Actons Lock, Regents Row | The repair works to Lock 7, Actons Lock, are no longer going ahead. We have reprioritised the resource to lock 65, Aspley, on the Grand Union Canal. This means, with reference to this notice, Lock 7 will now be open between the 6 January 2025 and the 7 February 2025. | No | 2025-01-06T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28249-lock-7-actons-lock-regents-row
28254 | Navigation Closure | West Midlands | Trent & Mersey Canal | Woodend Lock 20, Fradley | A navigation and towpath closure is required to reline the top lock gate and replace the heads and heels on the bottom lock gate. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28254-woodend-lock-20-fradley
28255 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Lock 2 Diglis, Worcester | The works at Lock 2 Diglis have been completed ahead of schedule. This means the navigation and towpath are no longer closed to facilitate these works. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-25T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28255-lock-2-diglis-worcester
28256 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Gregorys Mill Lock 5, Worcester | A navigation and towpath closure is required for bottom lock gate replacements. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28256-gregorys-mill-lock-5-worcester
29091 | Advice | London & South East | Grand Union Canal | Culvert 164, Abbots Langley | We are pleased to advise that we have come up with a method for doing these works without the need for a closure. The work will continue as programmed without a stoppage. | No | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29091-culvert-164-abbots-langley
29094 | Advice | London & South East | Slough Arm (Grand Union Canal) | Reeds Bridge 2, Iver | Construction work at this location to install a new bridge has been disrupted and delayed due to the impact of ongoing issues related to third party services and utilities that need to be resolved before the new footbridge is constructed. Unfortunately, this is preventing us from carrying out the works in the new year as planned. However, we have used the time afforded by these delays to explore other options that have become available following changes in land use in the area which should allow us to undertake the work using a different method without closing the navigation for as long. We will undertake the works next year once the cutting has dried out to a satisfactory degree and are expecting that any interruption to the navigation would only be for a few days at a specific point in the construction work. We will issue an updated notice once we have confirmed the details and specific dates. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-11T09:00:00+00:00 | https://canalrivertrust.org.uk/notices/29094-reeds-bridge-2-iver
29097 | Navigation Closure | West Midlands | Old Main Line | Lock 13, Wolverhampton | A navigation and towpath closure are required for top and bottom gate replacements, full lock ladder rebuild, and brickwork repairs. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29097-lock-13-wolverhampton
28141 | Navigation Closure | North West | Macclesfield Canal | Bosley lock 10, near Bosley | A stoppage is required to replace the liners on the top and bottom gates to stop leakage. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28141-bosley-lock-10-near-bosley
28153 | Navigation Closure | West Midlands | Old Main Line | Lock 2, Wolverhampton | A stoppage is required for bottom lock gate replacements. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28153-lock-2-wolverhampton
28157 | Navigation Closure | West Midlands | Grand Union Canal | Lock 40 on the Hatton Flight, Hatton | A navigation and towpath stoppage are required for top and bottom lock gate replacements. We will also be doing a full lock ladder rebuild. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28157-lock-40-on-the-hatton-flight-hatton
29083 | Navigation Closure | West Midlands | Llangollen Canal | Pontcysyllte Aqueduct, Trevor | The Pontcysyllte Aqueduct works have been completed ahead of schedule. This means the navigation is no longer closed to facilitate these works. | Yes | 2025-01-06T09:00:00+00:00 | 2025-03-06T15:00:00+00:00 | https://canalrivertrust.org.uk/notices/29083-pontcysyllte-aqueduct-trevor
28189 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Wash wall repair at Tunnel End bridge 61, Marsden | The works at this location have been delayed due to the installation of the fabric dam. The new end date for this closure will be the 21 February 2025. | Yes | 2025-01-13T08:00:00+00:00 | 2025-02-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28189-wash-wall-repair-at-tunnel-end-bridge-61-marsden
28204 | Navigation Closure | East Midlands | River Soar | Lock 45, Birstall Lock, Birstall | We apologise for having to extend this closure by an additional two weeks. Despite continued efforts on site, we have not been able to recover the delays to the works at Birstall Lock 45, initially caused by the navigation being frozen, then a few weeks later the site was flooded. These delays prevented us from getting our floating plant and equipment to site ready to start works on the 13 January 2025. We have reviewed the works specification to understand if anything can be done to reduce the remaining time needed on site. The works at Lock 45 are extensive, involving not just the replacement of the top and bottom lock gates, but also include repairs to the lock floor and brickwork repairs to the lock chamber walls. We have already brought in sub-contractors to support us but the lime mortar and concrete being used will need time to cure/set properly once that element of the work starts. We are unable to reduce the scope of works and without this extension we would require another closure at this site in a future year, incurring significant additional costs and local impacts. Deferring at this late stage is not possible as both sets of lock gates have been removed and would also mean incurring abortive costs to the project including plant hire and contractor costs. Given this we have taken the decision to continue the works and extend the stoppage by two weeks to complete all the works on site. We will continue to make every effort to reduce this extension period where we can through additional resource and hours worked and will update further if the timescale for the work reduces. The new end date for this closure will be the 28 March 2025. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28204-lock-45-birstall-lock-birstall
28205 | Navigation Closure | East Midlands | River Soar | Turnover Bridge 15, Birstall, | A navigation and towpath stoppage are required to repair brickwork on the towpath side abutment. This work will run alongside the closure at Lock 45, Birstall. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28205-turnover-bridge-15-birstall-
28233 | Navigation Closure | London & South East | Grand Union Canal | Lock 28, Grove Lock Marina, Leighton Buzzard | A stoppage is required to carry out replacement of the top and bottom lock gates. | No | 2025-01-13T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28233-lock-28-grove-lock-marina-leighton-buzzard
28762 | Navigation Closure | London & South East | Waterworks River | Bridgewater Road Bridge, Stratford Marsh | A Temporary bridge structure will be installed downstream of Bridgewater Road Bridge to accommodate these works. | Yes | 2025-01-13T08:00:00+00:00 | 2025-01-17T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28762-bridgewater-road-bridge-stratford-marsh
29107 | Navigation Closure | North West | Liverpool Link | Brunswick Dock, Liverpool | Following on from our last update, we have since been informed the manufacturer are experiencing delays with the new cylinder rod which will add an extra week onto this closure. We will continue to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologise for having to extend this closure to the 20 March 2025. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29107-brunswick-dock-liverpool
29174 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 83, of the Wigan Flight, Wigan | A navigational closure is required to refurbish Lock 83. | No | 2025-01-13T08:00:00+00:00 | 2025-02-03T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29174-lock-83-of-the-wigan-flight-wigan
29946 | Navigation Closure | North West | Trent & Mersey Canal | Lock 61, Cardboard Lock - Off Side | We’re really sorry that the repairs at Lock 61 are taking longer than planned and that we haven’t been able to re-open the canal today. Navigation will now reopen on Monday 20th January. Once our team have finalised the repairs to the lock. On Monday our team will work along side our scaffolding contractor to remove the access scaffolding allowing us to test the repairs, the canal will reopen soon afterwards. We’re truly sorry for any inconvenience this may have caused to your plans this weekend. | No | 2025-01-13T08:00:00+00:00 | 2025-01-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29946-lock-61-cardboard-lock-off-side
30458 | Navigation Closure | East Midlands | River Soar | Bridge 36 - Towpath support wall repairs | Following a review of project methodologies, we can complete these works from the 18 March 2025 as a restriction. Unfortunately, whilst dewatering the navigation the canal wall north of the bridge slipped, this means the navigational restriction will need to run until the 11 April to facilitate these works. The navigation will be restricted in width due to a crane boat and tug being moored up. We believe wide beam craft should still be able to pass. The towpath will be closed from the 31 March to the 11 April 2025. *Please note this web notice will be updated on the 18 March to reflect that its no longer a navigational closure. | No | 2025-01-13T08:00:00+00:00 | 2025-04-11T16:00:00+01:00 | https://canalrivertrust.org.uk/notices/30458-bridge-36-towpath-support-wall-repairs
29090 | Navigation Closure | London & South East | Regent's Canal | Islington Tunnel | Please be advised, we have reviewed the necessary inspection work for the tunnel, and we can undertake this with some short restrictions on day passages or overnight, therefore the stoppage has been removed. | No | 2025-01-14T16:00:00+00:00 | 2025-01-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29090-islington-tunnel
28183 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Railway Bridge 2, next to Colne Bridge Lock 2 | The works at this location have been extended due to delays in the plan as a result of low water levels which meant the third party contractor had to vacate the pontoon and stop working for safety reasons. The new end date for this closure will be the 20 March 2025. We will work with the contractor to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologise for the inconvenience this may cause. | Yes | 2025-01-16T08:00:00+00:00 | 2025-03-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28183-railway-bridge-2-next-to-colne-bridge-lock-2
28174 | Navigation Closure | North West | Peak Forest Canal | Service Crossings, attached to under side of Bridge 2, Dog Lane Bridge, Dukinfield | A stoppage is required to allow contractors working for Cadent gas, to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2025-01-20T08:00:00+00:00 | 2025-02-03T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28174-service-crossings-attached-to-under-side-of-bridge-2-dog-lane-bridge-dukinfield
28202 | Navigation Closure | East Midlands | Grand Union Canal | Lock 13, Long Buckby Wharf, Whilton, Daventry | Despite continued efforts on site, we have not been able to recover the delays in starting the works at Buckby Lock 13, initially caused by the knock-on effect of the delays at Whetstone Lock (the teams previous project) and then by the navigation being frozen. The works at Lock 13 are extensive, involving not just the replacement of the top and bottom lock gates, but also the lock ladder extensions (for safety reasons) and brickwork repairs to the lock chamber walls. We have brought in additional sub-contractors to support the brickwork repairs and ladder replacements, but given the delays there is a risk that not all the planned work will be delivered. Recognising that the national winter stoppage programme across the Trust ends on 14 March 2025 we have extended the stoppage end date at Buckby to then to try and get as much of the planned work completed as possible. We apologise for having to extend this closure by an additional week. The new closure end date is the 14 March 2025 | Yes | 2025-01-20T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28202-lock-13-long-buckby-wharf-whilton-daventry
28203 | Navigation Closure | East Midlands | Grand Union Canal | Lock 12, Long Buckby Wharf, Whilton, Daventry | Could we please ask for minimal use of Buckby Locks 7 through to 11 unless necessary. This is to help control the water levels around our construction site. Thank you in advance. | Yes | 2025-01-20T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28203-lock-12-long-buckby-wharf-whilton-daventry
28720 | Navigation Closure | North West | Macclesfield Canal | Sluice 8, Bollington near Clarence Mill Footbridge 26A | The original plan for this closure was to install a portadam within the canal to undertake the works. Our Contractor has confirmed that the works can be completed without the need for a Portadam so a navigational closure is no longer required at this sluice. | No | 2025-01-20T08:00:00+00:00 | 2025-01-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28720-sluice-8-bollington-near-clarence-mill-footbridge-26a
30551 | Navigation Closure | Yorkshire & North East | Sheffield & Tinsley Canal | Bacon Lane Bridge, Sheffield | The third party works at Bacon Lane Bridge have been completed ahead of schedule. Please note the navigation is still closed at Tinsley Lock 12. For more information please follow this link - Tinsley Lock 12, Sheffield. ¦ Canal & River Trust | No | 2025-01-20T08:00:00+00:00 | 2025-02-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30551-bacon-lane-bridge-sheffield
29942 | Advice | North West | Trent & Mersey Canal | Lock 63, Clear Water Lock - Towpath Side | We would like to advise you of this planned work to Clear Water Lock, 63. This will not close or restrict the navigation as the adjacent paired lock is available. From the 20 January 2025 to the 31 January 2025, we will be doing repair works to the ground and gate paddles. | No | 2025-01-20T08:00:00+00:00 | 2025-01-31T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29942-lock-63-clear-water-lock-towpath-side
28154 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 22 West, Uppermill | We are pleased to advise, the works at Lock 22 West Uppermill, have been completed ahead of schedule. | No | 2025-01-20T08:00:00+00:00 | 2025-02-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28154-lock-22-west-uppermill
28755 | Navigation Closure | London & South East | Oxford Canal | Lock 29, Banbury | The works at Lock 29 Banbury, have been completed ahead of schedule. This means the navigation is no longer closed to facilitate these works. | No | 2025-01-21T08:00:00+00:00 | 2025-02-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28755-lock-29-banbury
28207 | Navigation Closure | West Midlands | Caldon Canal | Hazelhurst Lock 10, Denford (Top Lock) | A navigation and towpath closure are required for ground paddle leak repairs. | Yes | 2025-01-27T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28207-hazelhurst-lock-10-denford-top-lock
28242 | Navigation Closure | West Midlands | Montgomery Canal | Graham Palmer Lock, Lower Frankton | A navigation and towpath closure is required for top and bottom end lock gate replacements. We will also be repairing the coping stones. | Yes | 2025-01-27T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28242-graham-palmer-lock-lower-frankton
28765 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Llanfoist Embankment, Bridge 95A - Bridge 96 | We have completed the first phase of these investigation and construction works which were delayed because of challenges sourcing specialist equipment and agreeing the temporary works for this location. We are now progressing the second phase of the works by working weekends and longer hours to reduce further delays. We apologise for the delay - but despite our best efforts, the stop planks now acting as the temporary dams, will not be removed until Sunday 16 March. We are hopeful that the canal will be fully re-filled with water and re-opened to navigation a few days later. | Yes | 2025-01-27T08:00:00+00:00 | 2025-03-16T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28765-llanfoist-embankment-bridge-95a-bridge-96
30613 | Navigation Closure | East Midlands | Grand Union Canal | Lock 15 Stoke Bruerne | We are pleased to advise, the works at Lock 15 Stoke Bruerne, have been completed ahead of schedule. | No | 2025-01-27T08:00:00+00:00 | 2025-02-04T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30613-lock-15-stoke-bruerne
29086 | Navigation Closure | West Midlands | Montgomery Canal | Frankton Lock 4 | Following further investigations on site we need longer to ensure we complete all the grouting work required. This will extend the closure by 1 week to 21 February 2025. The navigation is already closed at Graham Palmer lock through to the 21 February 2025. | No | 2025-01-27T08:00:00+00:00 | 2025-02-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29086-frankton-lock-4
28733 | Navigation Closure | North West | Macclesfield Canal | Sluice 10, Near Higherfold Bridge 33, Higher Hurdsfield | Unfortunately, the works planned at sluice 10, between bridge 30 Woods Bridge and bridge 33, Higherfold Bridge have been delayed. The contractor’s plant/equipment has been delayed in getting to site. The new closure date is the 29 January 2025, the end date remains the same, 07 February 2025. | No | 2025-01-29T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28733-sluice-10-near-higherfold-bridge-33-higher-hurdsfield
28198 | Navigation Closure | London & South East | Grand Union Canal | Colne Valley Viaduct, High Speed 2, south of Moorhall Road, Denham | We have been advised that HS2 are ahead of schedule and have already completed this section of planned works, so this closure is no longer needed. Therefore, the canal and towpath will no longer be closed to facilitate these works. | Yes | 2025-02-03T08:00:00+00:00 | 2025-02-14T10:00:00+00:00 | https://canalrivertrust.org.uk/notices/28198-colne-valley-viaduct-high-speed-2-south-of-moorhall-road-denham
28200 | Navigation Closure | West Midlands | Caldon Canal | Hazelhurst Lock 11 (Middle Lock), Denford | Despite our best efforts the works to Hazelhurst Lock 11, need to be extended. The lock gates were delayed when returning from the workshop following their refurbishment and this has had a knock on effect to the planned works. Unfortunately, we will need to extend this closure to the 21 March 2025. We will continue to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologies for the inconvenience this may cause. | Yes | 2025-02-03T08:00:00+00:00 | 2025-03-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28200-hazelhurst-lock-11-middle-lock-denford
28209 | Navigation Closure | North West | Trent & Mersey Canal | Lock 57, Hassall Green | A stoppage is required for replacement of the bottom lock gates. We will also fit new liners to the top gate and cill to prevent further leakage. | No | 2025-02-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28209-lock-57-hassall-green
28734 | Navigation Closure | North West | Macclesfield Canal | Sluice 12, Gurnett Aqueduct, Macclesfield | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2025-02-03T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28734-sluice-12-gurnett-aqueduct-macclesfield
30023 | Navigation Closure | Wales & South West | Gloucester & Sharpness Canal | Purton Upper Safety Gates | Unfortunately due to contractual issues, the diving contractor was not available to start works on the 27th January and the survey had to be delayed for a week. The diving survey will now commence on 3rd February and be completed by the 7th February 2025. | No | 2025-02-03T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30023-purton-upper-safety-gates
29087 | Navigation Closure | London & South East | Grand Union Canal | Cassio Bridge near lock 78 | A stoppage is required for grouting the lock chamber wall. | No | 2025-02-03T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29087-cassio-bridge-near-lock-78
29941 | Advice | North West | Trent & Mersey Canal | Lock 64, Saw Pit Lock - Off Side | We would like to advise you of this planned work to Saw Pit Lock, 64. This will not close or restrict the navigation as the adjacent paired lock is available. From the 03 February 2025 to the 14 February 2025, we will be doing repair works to the ground and gate paddles. | No | 2025-02-03T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29941-lock-64-saw-pit-lock-off-side
30758 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 77, of the Wigan Flight, Wigan | We would like to advise you of this additional closure within the Winter Works Programme. We started to work on Lock 77 before Christmas but did not have the full 7 weeks to complete the works due to delays getting to site after an over run at Prescott Embankment. When on site, following the dewater, it was discovered that more sections of the wall were found to have failed than originally thought. In order to complete these works and have the Wigan Flight open by the 15 March we need to start these works as soon as possible. This closure will start today and the Wigan Flight will be open again on the 15 March 2025 when all the works on the flight have been completed. | No | 2025-02-03T13:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30758-lock-77-of-the-wigan-flight-wigan
29103 | Navigation Closure | London & South East | Hertford Union Canal | Accommodation Bridge 10, Footbridge, Hackney Wick, London. | These Third party works will be removed from the winter works programme as they are not ready to meet these dates. We have been informed they are likely to add these works into next winters programme of works or request for a nighttime closure. Therefore, the canal will no longer be closed to facilitate these works. | Yes | 2025-02-05T08:00:00+00:00 | 2025-02-05T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29103-accommodation-bridge-10-footbridge-hackney-wick-london
29968 | Navigation Closure | North West | Macclesfield Canal | Lock 8, Bosley | We would like to advise you of this additional closure to the Winter Works Programme. The repair works needed to Lock 8 have been prioritised over Lock 6 thus deferring Lock 6 from the programme. We will be doing repairs to the balance beams, cill, collars and mitre on Lock 8. The works will take place as a navigational closure between the 10 February 2025 and the 14 March 2025 (inclusive) | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29968-lock-8-bosley
28236 | Navigation Closure | London & South East | Grand Union Canal | Lock 89, Cowley Lock, Cowley | The bottom gates at Cowley Lock were lifted in on 11 March and need to be set in place and adjusted to get the gates to fit correctly. The cills also need fitting and adjustment. Unfortunately, we will not be able to open by 14 March as there is too much work remaining to be done. We will keep boaters waiting at the lock verbally updated on progress. Please accept our sincere apologies for this extension, the team on site are on track to finish by 21 March but will make every effort to finish sooner if possible. | No | 2025-02-10T08:00:00+00:00 | 2025-03-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28236-lock-89-cowley-lock-cowley
28761 | Navigation Closure | West Midlands | Walsall Canal | Lock 3, Ryders Green, Near West Bromwich | A stoppage is required for a Bywash channel rebuild. | Yes | 2025-02-10T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28761-lock-3-ryders-green-near-west-bromwich
29173 | Navigation Closure | West Midlands | Caldon Canal | Bank protection works, Etruria | The bank protection works between Locks 1 and 3 Etruria, have been completed ahead of schedule. This means the navigation and towpath are no longer closed to facilitate these works. | Yes | 2025-02-10T08:00:00+00:00 | 2025-02-17T08:00:00+00:00 | https://canalrivertrust.org.uk/notices/29173-bank-protection-works-etruria
29175 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 73, of the Wigan Flight, Wigan | Whilst undertaking the planned works it became apparent that there was a large sink hole behind the concrete apron and under the offside tailgate post, unfortunately this means we need to extend the closure by a few days to complete these works and allow the concrete to cure. The new end date for this closure will be the 17 March 2025. We apologies for the inconvenience this may cause. | No | 2025-02-10T08:00:00+00:00 | 2025-03-17T17:00:00+00:00 | https://canalrivertrust.org.uk/notices/29175-lock-73-of-the-wigan-flight-wigan
28150 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 2 West, Stalybridge | We apologise for having to extend this closure for an additional week. We have been unable to secure access from third parties to access the work by land to deliver and lift the gates in - and are having to revert to doing everything from the water and it will now take an extra week to complete everything on site. The new start date for this closure will be the 14 February 2025. The end date will be extended to the 21 March 2025. | No | 2025-02-14T08:00:00+00:00 | 2025-03-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28150-lock-2-west-stalybridge
28177 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 2 East, Coal Wharf lock, Huddersfield | A stoppage is required to allow Lock gate replacement and lock chamber repairs. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28177-lock-2-east-coal-wharf-lock-huddersfield
28178 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Lock 4, Longlands, Deighton, Huddersfield | The works at this location have been extended. Whilst working on lock 4 it became apparent that more fabricating needed to be done to the paddles than originally planned. The Trust has made the decision to do this work now to prevent us closing again in the near future. Unfortunately, this has impacted the programme and extended it by one week. The new end date for this closure will be the 20 March 2025. We will continue to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologise for the inconvenience this may cause. | No | 2025-02-17T08:00:00+00:00 | 2025-03-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28178-lock-4-longlands-deighton-huddersfield
28179 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Lock 5 Turnpike, Huddersfield | The works at this location have been extended. The works were set back as the result of a theft from site and then whilst working on the lock it became apparent that more work was needed to the tail gate floor area. The Trust has made the decision to do this work now to prevent us closing the lock again in the near future. Unfortunately, this has impacted the programme and extended it by one week. The new end date for this closure will be the 20 March 2025. We will continue to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologise for the inconvenience this may cause. | No | 2025-02-17T08:00:00+00:00 | 2025-03-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28179-lock-5-turnpike-huddersfield
28214 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 80, Copse, Kintbury | Please be advised the closure at Copse Lock 80 is no longer going ahead due to lack of resource. We will, later in the year, replace the lock beams under a navigational restriction, and the rest of the works will be completed in another winter programme. This means the navigation will no longer be closed to facilitate these works. | No | 2025-02-17T08:00:00+00:00 | 2025-01-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28214-lock-80-copse-kintbury
28729 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 33 East, near Marsden | We are sorry that the dates of this navigation closure need to change. This is due to the works now extending within the curtilage to the tail bridge which is listed, and is located close to this lock. The processing of this application will prevent us delivering the works within the original dates, and so, new start and end dates have been programmed to complete the work within this 2024/25 winter programme. | Yes | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28729-lock-33-east-near-marsden
28234 | Navigation Closure | London & South East | Grand Union Canal | Lock 31, Horton Lock, near Slapton | A stoppage is required to carry out replacement of the top and bottom lock gates. We are also repairing the brickwork in the lock chamber. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28234-lock-31-horton-lock-near-slapton
28763 | Navigation Closure | London & South East | Waterworks River | Bridgewater Road Bridge | A stoppage is needed so the existing Bridgewater Road Bridge can be demolished and new bridge structure installed at same location. | Yes | 2025-02-17T08:00:00+00:00 | 2025-03-09T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28763-bridgewater-road-bridge
29098 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Lock 28, Stoke Prior, Near Bromsgrove | A navigation and towpath closure are required for bottom end gate replacements and a full lock ladder rebuild. The whole flight will be closed for safety reasons. | Yes | 2025-02-17T08:00:00+00:00 | 2025-03-14T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/29098-lock-28-stoke-prior-near-bromsgrove
28148 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 12 West, Mossley | The repair works at Lock 12 West, have been completed ahead of schedule. This means the navigation is no longer closed to facilitate these works. | No | 2025-02-17T08:00:00+00:00 | 2025-02-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28148-lock-12-west-mossley
29940 | Advice | North West | Trent & Mersey Canal | Lock 42, Limekiln Lock - Towpath side | Following a review of project methodologies, we are now able to do these works within a 4-hour window. We will update this notice with the new dates as soon as they are confirmed. Please note: This will not restrict navigation as the adjacent paired lock is available. | No | 2025-02-17T08:00:00+00:00 | 2025-02-17T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29940-lock-42-limekiln-lock-towpath-side
28712 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Culvert 14, between lock 20 east and lock 21 east, Slaithwaite | The culvert works between Lock 20 East and Lock 21 East have been completed ahead of schedule. This means the navigation is no longer closed to facilitate these works. | No | 2025-02-20T08:00:00+00:00 | 2025-03-12T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28712-culvert-14-between-lock-20-east-and-lock-21-east-slaithwaite
28756 | Navigation Restriction | London & South East | Oxford Canal | Bridge 181, Scrooby's Lift Bridge, Kings Sutton | Due to flooding and high water on this length of canal, we do not think it will be possible to install fabric dams to dewater the canal, we have therefore agreed to descope the work to removing offside vegetation and removing the bridge deck to relieve pressure on the offside wall. This work can now be done as a restriction on weekdays only between the 24 February 2025 and the 28 February 2025. Navigation will possible – Mon – Before 9:00am, between 13:00 and 14:00pm and after 16:00pm Tue – Before 9:00am, between 13:00 and 14:00pm and after 16:00pm Wed – Before 9:00am, between 13:00 and 14:00pm and after 16:00pm Thurs– Before 9:00am, between 13:00 and 14:00pm and after 16:00pm Fri– Before 9:00am, between 13:00 and 14:00pm and after 16:00pm Sat – Open as normal Sun - Open as normal | No | 2025-02-24T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28756-bridge-181-scroobys-lift-bridge-kings-sutton
28738 | Navigation Closure | London & South East | Regent's Canal | 100m east of Bridge 31, Oblique Bridge, near St Pancras | We have been informed by a third party that these works have been revised causing the dates to change. We seek to avoid changing dates, but whilst elements of this are outside our control being a third party, this change does have the benefit of bringing the closures in this area into the same timeframe. The new navigation and towpath closure will be from 6pm on the evening of the 28 February 2025 through to 5am on the 2 March 2025 | Yes | 2025-02-28T18:00:00+00:00 | 2025-03-02T05:00:00+00:00 | https://canalrivertrust.org.uk/notices/28738-100m-east-of-bridge-31-oblique-bridge-near-st-pancras
28193 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 32 East, by Sparth reservoir | A stoppage is required for Lock gate heel timber repairs. | No | 2025-03-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28193-lock-32-east-by-sparth-reservoir
30778 | Navigation Restriction | London & South East | Oxford Canal | Chisnell Lift Bridge 193 | Work at Scroobys Lift Bridge (181) have been descoped due to flooding and high water, therefore whilst the crane boat is in the area we are looking to make use of it and fit the already build new Chisnell lift bridge. Lifting the bridge deck in place can be completed under a restriction with a maximum delay to navigation of 4 hours. The restriction will start on the 3 March 2025 and run through to the 7 March 2025. Please approach the site with caution and take advice from staff on site. | Yes | 2025-03-03T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30778-chisnell-lift-bridge-193
28250 | Navigation Closure | Wales & South West | River Severn Navigation | Lock 2, Gloucester Lock, The Docks, Gloucester | We have reduced the scope of the post Christmas works at Gloucester Lock 2 to two weeks. The new closure dates are 3 March 2025 to 14 March 2025. Additional work to strengthen the existing stop log metal channel, in the river side of the lock, will be completed before Christmas as part of a one week closure. The navigation will be closed from the 4 November through to the 8 November 2024 (inclusive), open for the weekend (9 and 10 November) and closed again on the 11 November 2024 for these works to be completed. | Yes | 2025-03-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28250-lock-2-gloucester-lock-the-docks-gloucester
28144 | Navigation Closure | North West | Rufford Branch (L&L Canal) | Downstream of Lock 2, Rufford | The works downstream of Lock 2, Rufford have been completed. This means the navigation is no longer closed to facilitate these works. | No | 2025-03-03T08:00:00+00:00 | 2025-03-10T10:00:00+00:00 | https://canalrivertrust.org.uk/notices/28144-downstream-of-lock-2-rufford
29938 | Advice | North West | Trent & Mersey Canal | Lock 45, Kents Lock - Towpath side | We would like to advise you of this planned work to Kents Lock, 45. This will not close or restrict the navigation as the adjacent paired lock is available. From the 3 March 2025 to the 14 March 2025, we will be doing repair works to the ground and gate paddles. | No | 2025-03-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29938-lock-45-kents-lock-towpath-side
28212 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 91, Colthrop | The leak repair works to Colthrop Lock are underway and on plan. We would like to kindly remind customers that there is no passage through Lock 91 whilst these works take place. Once complete these works should help our boating customers pass through this lock more efficiently. | No | 2025-03-04T08:00:00+00:00 | 2025-03-05T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28212-lock-91-colthrop
30904 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Bath Flight from Lock 7, Bath Bottom Lock to Lock 13, Bath Top Lock | The Trust has had to remove this work from this year’s winter works programme. A revised date will be published in due course. We apologise for any inconvenience caused. | No | 2025-03-05T08:00:00+00:00 | 2025-03-05T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/30904-bath-flight-from-lock-7-bath-bottom-lock-to-lock-13-bath-top-lock
28740 | Navigation Closure | London & South East | Regent's Canal | 100m east of Bridge 31, Oblique Bridge, near St Pancras | We have been informed by a third party that these works have been revised causing the dates to change. We seek to avoid changing dates, but whilst elements of this are outside our control being a third party, this change does have the benefit of bringing the closures in this area into the same timeframe. The new navigation and towpath closure will be from 6pm on the evening of the 7 March 2025 through to 5am on the 9 March 2025. | Yes | 2025-03-07T18:00:00+00:00 | 2025-03-09T05:00:00+00:00 | https://canalrivertrust.org.uk/notices/28740-100m-east-of-bridge-31-oblique-bridge-near-st-pancras
28713 | Navigation Closure | West Midlands | Wyrley & Essington Canal | New road bridge to be constructed north of Yorks Bridge, Pelsall Common, Walsall. | A third party is constructing a new road bridge to the north of Yorks Bridge, Pelsall Common, Walsall. Due to technical issues with the structural piles and adverse weather conditions, their programme has been delayed, and they will not meet their previously agreed dates for the beam installation and canal closure. Their new closure dates are from 10 March 2025 through to 16 March 2025. | Yes | 2025-03-10T08:00:00+00:00 | 2025-03-16T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28713-new-road-bridge-to-be-constructed-north-of-yorks-bridge-pelsall-common-walsall
31025 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Between Lock 5 East and Lock 6 East | We would like to advise you of this additional closure to the Winter Works Programme. The offside retaining wall is in need of repair and with resource available we would like to take this opportunity to do these repairs to prevent further failure during the boating season. We will be closing the navigation on the 10 March through to the 21 March 2025. We apologise for the inconvenience this may cause customers. | No | 2025-03-10T08:00:00+00:00 | 2025-03-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/31025-between-lock-5-east-and-lock-6-east
31036 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 68, of the Wigan Flight, Wigan | Unfortunately we need to undertake additional works following reports of Lock 68 loosing water at the tailgate. We have been able to inspect the problem due to other works on the flight and have found a failed cill at Lock 68. The Wigan flight is currently closed to facilitate the works at Lock 73, the Lock 68 repair will require an extension to the closure. We are taking the opportunity to carry out other essential work on the locks currently and the cill works will commence as soon as the design is finalised. The flight will reopen by the 31 March 2025. We will continue to make every effort to reduce this extension period where we can and will update further if the timescale for the work reduces. We apologies for the inconvenience this may cause. | No | 2025-03-11T12:00:00+00:00 | 2025-03-31T16:00:00+01:00 | https://canalrivertrust.org.uk/notices/31036-lock-68-of-the-wigan-flight-wigan